## Sheet1
Nội dung các task đã, đang và sẽ thực hiện (Lưu ý tuần 11 hoặc 12 chốt hết Code, tuần 13 và 14 hoàn thiện các nội dung về doc và thay đổi code nếu cần
Code Project | Topic | Lịch gặp nhóm (Giờ - ngày trong tuần) theo lịch trên LMS | Student | Tuần 1 | Tuần 2 | Tuần 3 | Tuần 4 | Tuần 5 | Tuần 6 | Tuần 7 | Tuần 8 | Tuần 9 | Tuần 10 | Tuần 11 | Tuần 12 | Tuần 13 | Tuần 14
PAPV | Book Library management with flycam and code bar | Slot 1-2 Thứ 7 | Nguyễn Huỳnh Phú | Requirement Gathering Design Database | Usecase design Report 2 Web admin design | Design and code web admin(CRUD Bookgroup, CRUD Bookshelf) Usecase spec (Report 3) ERD Update database | Design and code web admin(CRUD Location, Drawer, Add book to drawer) System Architecture Design (Report 4) | Design and code web admin(CRUD Librarian, Manage Borrow Book) | Research stream video Design and code web admin(Borrow Book) Update usecase spec | Research stream video Design and code web admin(Return Book) Write test case | Update test case Complete web admin Update function return book | Complete web admin Update document | Validation for webadmin Test web admin base test case | Prepare powerpoint and presentation Hot fix web admin, update document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document
PAPV | Book Library management with flycam and code bar | Slot 1-2 Thứ 7 | Nguyễn Hữu Linh | Requirement Gathering Design Database | Usecase design Report 2 Update database | Build RESTful API and deploy to IIS(CRUD Bookgroup, CRUD Bookshelf) Usecase spec (Report 3) Non fuctional requirement (Report 3) Update database | Build RESTful API and deploy to IIS(CRUD Location, Drawer, Add book to drawer) Activity Diagram (Report 4) | Build RESTful API and deploy to IIS(CRUD Librarian, Manage Borrow Book) | Design and code mobile app(Update Profile) Implement SignalR Update usecase spec Update activity diagram | Design and code mobile app(Book detail) Write test case Update API(Borrow book, Return book) | Update test case Update UI for mobile app Update function return book | Complete mobile app, API Update document | Validation for mobile app, API Update document Test mobile app | Prepare powerpoint and presentation Hot fix mobile app, update document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document
PAPV | Book Library management with flycam and code bar | Slot 1-2 Thứ 7 | Trần Đăng Khánh | Research Flutter Research Python Report 1 | Research yolo v3 Requirement Gathering Report 2 | Collect data and train model for AI detect on yolo V3 Usecase spec (Report 3) Screen flow (Report 3) design and code mobile app(Feedback) | Collect data and train model for AI detect on yolo V4 Class diagram (Report 4) Design and code mobile app (add book to wishlist) | Collect data and train model for AI detect on yolo V5, build Python server on GPU | Build server AI detect Implement detect get box of barcode and read barcode Update usecase spec | Build server AI detect Implement how to know list barcode in a drawer Write unit test | Build server AI detect Implement how to know list barcode in a drawer Research deepsort | Complete server AI Test detect on video 4K Record about performance detect | Test AI Comple AI server Update document | Prepare powerpoint and presentation Hot fix system AI, update dataset Update document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document
PAPV | Book Library management with flycam and code bar | Slot 1-2 Thứ 7 | Trịnh Tiến Hoàng | Requirement Gathering Report 1 Research Flutter | Design mobile app Report 2 Usecase design | Design and code mobile app(Login, Signup) Use case diagram (Report 3) Usecase spec (Report 3) Update use case | Design and code mobile app(Scan QR code) Sequence diagram (Report 4) Update usecase | Update diagram, design and code mobile app( search book, view profile) | Research paper AI Create label for dataset Update usecase spec | Update activity diagram, sequence diagram Design and code mobile app (Return book, Borrow Book) Write unit test | Write user guide in report 6 Update UI for mobile app Update feature list and document | Complete document Comple mobile app | Validation for mobile app, API Update document Test mobile app | Prepare powerpoint and presentation Hot fix mobile app, update document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document | Prepare powerpoint and presentation Testing and hot fix Complete document